## Slide 1: Risk Plan
risk | monitoring/control | response | impact | likelihood | Occurence
Illness | make your employees have a healthy lifestyle | overtime for other employees / hire external sources | medium / time | high | no
Code loss | use version control (git) | write new code | very high / time | Very low | yes
New requirement | test requirement and get an estimate | implement or reject requirement | high / time | high | yes
Existing requirement proves to be wrong | during development test all requirements | change existing requirement and adapt code | high / time | high | no
Hardware defect | Use fairly new and maintained hardware | Buy new hardware | low /cost | low | no
Wrong time estimates | Check development according to time plan | Edit time plan | high / time | high | yes

## Slide 2: Risk: Code Loss
Monitoring/control: use version control (git)
Response: write new code
Impact: very high
Likelihood: very low
Reason: Wrong use of Git
For the future: Git training for all employees

## Slide 3: Risk: New Requirement
Monitoring/control: test requirement and get an estimate
Response: implement or reject requirement
Impact: high
Likelihood: high
Reason: Change request by MATSECOM
For the future: Not preventable

## Slide 4: Risk: Wrong time estimates
Monitoring/control: Check development according to time plan
Response: Edit time plan
Impact: high
Likelihood: high
Reason: Setup took longer than expected
For the future: Take setup in mind/ Experience will prevent this